## Project Planner
Eco-friendly Home energy saving System
This Gantt chart shows the project implementation plan until 9th February |  |  |  |  | Period Highlight: | 9 |  |  | Plan Duration | [5 empty] | Actual Start |  |  |  |  | % Complete |  |  |  |  | Actual (beyond plan) | [7 empty] | % Complete (beyond plan)
Tasks | PLAN START | PLAN DURATION | ACTUAL START | ACTUAL DURATION | PERCENT COMPLETE | PERIODS
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60
Interview Potential End Users | 2 | 5 | 2 | 5 | 10%
Gather requirements | 8 | 3 | 8 | 3 | 20%
First draft of program | 12 | 3 | 12 | 3 | 25%
Gather Hardware devices | 12 | 1 | 12 | 1 | 26%
Gather prototype materials | 15 | 1 | 15 | 1 | 30%
Test run of first draft of software | 16 | 3 | 16 | 3 | 40%
Test run of individual hardware | 16 | 3 | 16 | 3 | 50%
Test run of second draft of software | 21 | 4 | 21 | 4 | 60%
Assemble Hardware | 22 | 2 | 22 | 2 | 70%
Debug all Hardware I/O | 25 | 2 | 25 | 2 | 75%
Debug Final Version of Software | 29 | 4 | 29 | 4 | 80%
Test run of final product | 36 | 4 | 36 | 4 | 90%
Debug of final product | 37 | 3 | 37 | 3 | 95%